## Estimation Sheet
SAMPLE ELEARNING PROJECT ESTIMATION SHEET
Note: These are sample numbers only for a Finished 1 hour Level 1 eLearning course. Please modify to fit your specific project and your hourly/project rates
CONTENT DEVELOPMENT ESTIMATES
Phases | Tasks | Avg. Time Spent on Task (in hours) | Hourly Rate | Task Cost (Calculated as Avg. Time Spent on Task x Hourly Rate)
CREATION | Front End Analysis | 8 | 50 | 400
| Instructional Design | 10.4 | 50 | 520
| Storyboarding | 8.8 | 50 | 440
| Other | 0.8 | 50 | 40
PRODUCTION | Graphic Incorporation | 9.6 | 40 | 384
| Video Incorporation | 4.8 | 40 | 192
| Audio Incorporation | 4.8 | 40 | 192
| Authoring/Programming | 14.4 | 40 | 576
QUALITY CONTROL | QC Testing | 5.6 | 25 | 140
| Pilot Testing | 3.2 | 25 | 80
PROJECT MANAGEMENT | Project Management | 4.8 | 25 | 120
| Manage SME/Stakeholder Reviews | 4.8 | 25 | 120
Content Development SubTotal > |  | 80 |  | 3204
MISCELLANEOUS TASK ITEMS ESTIMATE
Item Description | Comments | Estimated Cost
Professional Audio Narration | Expect 20 minutes total @$20 per finished minute | 400
Graphics/Image Procurement | Expect to purchase ~10 images from iStock | 20
Add New Item Here |  | 0
Add New Item Here |  | 0
Add New Item Here |  | 0
Add New Item Here |  | 0
Add New Item Here |  | 0
Miscellaneous Items SubTotal > |  | 420
ESTIMATE BREAKDOWN (calculated from above)
Content Development Cost | 3204
Miscellaneous Items Cost | 420
Administrative Overhead (10%) | 362.4
Your Total Quote Estimate is >
3986.4